## PhD Thesis Deadline Calc
PhD Thesis Timeline Calculator
DATE/DEADLINE
| WHAT IS YOUR PREFERRED PhD EXAMINATION DATE? (DD-MMM-YY) | 2021-08-09 | *Guidelines and FAQ's can be found under the second excel sheet 'Instructions' | 8 | 5 | 9 | OK
STEP | TASK | DATE/DEADLINE
1 | Supervisory committee signs Thesis Readiness form and recommends PhD thesis is ready for exam preparation | 2021-05-17
2 | External examiner and university examiner nomination forms submitted to SGPS | 2021-05-31
3 | Request to Schedule a PhD Oral Exam form and thesis submitted to SGPS (recommended 9 weeks before exam but no less than 8 weeks) | 2021-06-07
4 | Thesis sent to examining committee members by SGPS (no less than 8 weeks before exam) | 2021-06-14
5 | External and University Examiner's reports due (10 days before exam) | 2021-07-30
6 | FINAL PhD EXAMINATION DATE | 2021-08-09
7 | Chair's report due (1 week after exam) | 2021-08-16
8 | "If Minor Revisions" Deadline | 2021-09-06 | *This date is in a new term. Students are responsible for ensuring fees are paid in full. | 9 | 9 | 6 | OK
9 | "'If Major Revisions" Deadline | 2022-02-07 | *This date is in a new term. Students are responsible for ensuring fees are paid in full. | 2 | 1 | 7 | OK

## Instructions and FAQs
Instructions: | Double click the green box (C4 on Sheet 1) and enter your desired examination date using the following format (dd-mmm-yy). Suggested dates will be generated for when each step should be completed in order to defend by the preferred examination date.
Review important dates and deadlines on the Graduate Studies website: | SGPS Timelines and Deadlines
FAQ's
What is the Thesis Readiness Form? | The Regulation/Policy states that the supervisory committee must recommend to the GPD/Dean of SGPS whether the thesis is ready to move to oral examination 3 months before a tentative examination date. The 3 month guideline refers to the supervisory committee feeling confident that the body of the work is sufficient to proceed to defence, while the thesis document may not be the final draft. Further revisions can be made to the thesis after this recommendation is made to the GPD but if the thesis is found to be ready for defence, the revisions should not be of substantive nature. The Thesis Readiness form should act as a prompt for committee’s to think about the oral defence examiner(s), a date that works for all parties and to ensure the thesis is sent out in an appropriate timeframe. It should also help to set realistic timelines for students and supervisors when considering thesis submission deadlines etc.
Review Minor and Major Revision Deadlines and compare with the final thesis package deadlines for submission to SGPS | If the student cannot submit the thesis to the program office by the final thesis package deadline, they will be subject to fees in the following term.