## Calculator & Timeline
INSTRUCTIONS: Enter your required completion date in cell C5 and the estimated days to complete revisions in cell C7. Refer to notes in column E for more information.
Click this cell to view the Master's thesis deadlines on our website.
NOTES
What is your required completion date? |  | 2026-04-22 |  | This is the day you submit your final thesis package, after your defence and after any required revisions have been completed and approved. If you wish to graduate on the regular term cycle: Enter a date no later than the Master's Thesis Deadline for the semester you wish to graduate, available on our website linked above (cell A2). This deadline must be met to avoid incurring next-term fees. If you need proof of graduation by a specific date (e.g., for student visa expiry, employment, etc.): Enter a date at least 2 weeks BEFORE your needed graduation date. (e.g., If you require proof of completion by November 30, enter November 16 or earlier.)
How much time will you need to complete revisions after your defence? |  | 14 | days | Revisions won't be determined until the time of your defence, but your estimate will depend on how much time you have to devote to your revisions and how much time your supervisor/reviewer will need to approve them. SGPS recommends at least 14 days, but you should discuss this with your supervisor now, while planning for your completion. Maximum times for completing revisions are 4 weeks for minor revisions and 6 months for major revisions.
STEP | TASK | DATE/DEADLINE |  | NOTES | 2026-02-01 | 0 | Feb 1
1 | Form 2M submitted at least 5 weeks prior to defence | 2026-03-04 |  | To be received by this date, it should be initiated approximately 1 week earlier. Supervisors should contact the Faculty graduate program office for assistance. | 2026-03-04 | 20 | Mar 4 Submit form 2M
2 | Thesis submitted to SGPS at least 5 weeks prior to defence | 2026-03-04 |  | You or your supervisor should submit to the Faculty graduate program office. | 2026-03-04 | 10 | Mar 4 Submit thesis
3 | Defence | 2026-04-08 |  | Following your defence, begin working on any required revisions. Instructions for submitting your final thesis package will be shared with you by SGPS. | 2026-04-08 | 30 | Apr 8 Defence
4 | Submit final thesis package | 2026-04-22 |  | Refer to the the current year Master's Thesis Deadlines, available on our website linked above, for the term submission deadline. If your thesis package is not received by SGPS by the submission deadline, you will be responsible for applicable fees in the following term. | 2026-04-22 | 20 | Apr 22 Submit final thesis package
5 | Earliest possible date for expedited degree conferral (if applicable) | 2026-05-06 |  | Applies if you need proof of graduation by a specific date outside the regular term cycle; this is the earliest possible date your degree can be conferred/proof of completion can be available. If you require proof of completion earlier than this date, please adjust your required completion date (cell C5) accordingly. | 2026-05-06 | 10 | May 6 Earliest possible degree conferral
[5 empty] | 2026-06-30 | 0 | Jun 30